## Sheet1
Team Valorant Timeframe
|  | PROJECT START |  | 2020-04-20
|  | PROJECT END |  | 2020-09-30
| WEEK |  |  | START | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEk 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | PHASE 2 | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | END PROJECT
| DAYS |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
Phase 1: Project PLANNING
TASK: | ASSIGN: |  | START: | FINISH:
START PROJECT |  |  | WEEK 1 | WEEK 1
DRAFT:
SKETCH OF UI | Wen/Tim |  | WEEK 4 | WEEK 4 | [27 empty] | DUE
ARTEFACT | Eenu/Tim |  |  | WEEK 4 | [27 empty] | DUE
ALLOCATE WORK | EVERYONE
RESEARCH | EVERYONE |  |  | WEEK 6 | bar: S to S
TEAM MEETING | EVERYONE |  | WEEK 1 | WEEK 16 | bar: S; S; S; S; S to S; S to S
PRESENTATION | Eenu/Tim/Wen |  | WEEK 5 | WEEK 6 | [41 empty] | DUE | bar: M to T
ASSIGNMENT 3 | EVERYONE |  | WEEK 3 | WEEK 6 | [41 empty] | DUE
END OF PHASE 1 |  |  | WEEK 6 | WEEK 6 | [41 empty] | DUE
Phase 2: Project PLANNING
TASK: | ASSIGN: |  | START: | FINISH:
START Phase 2 |  |  | WEEK 7 | WEEK 7 | [43 empty] | S: Due
APP DEVELOPMENT | Tyson/Tim |  | WEEK 7 | WEEK 16 | bar: F to S
UI/UX | Eenu/Tim/Wen |  | WEEK 7
CLOSED BETA |  |  | WEEK 10 | WEEK 12 | [43 empty] | S: Due; S: Due
BETA lLAUNCH | Tyson/Tim |  | WEEK 14 | WEEK 14 | [43 empty] | M: Due
FULL RELEASE |  |  | WEEK 16 | WEEK 16 | [43 empty] | S: Due
MARKETING | WEN |  | WEEK 9 | WEEK 12
SERVER SETUP | Tyson
DOCUMENTATION | EVERYONE |  | WEEK 1 | WEEK 16
END OF PROJECT |  |  | WEEK 16 | WEEK16